## Instructions
1. Stakeholder
List the name, position or group of the stakeholder (internal or external) relevant to the project or initiative.
Include departments or teams if necessary. Some Stakeholder Registers assign a number to each stakeholder.
Example:
Jennie Rogers (Program Manager)
Marketing Department Lead
Local Health Authority
2. Role
Specify the stakeholder’s role in the project or program, including their responsibilities.
Example:
Executive Sponsor
Project Manager
Vendor Representative
3. Attitude
Describe the stakeholder’s overall attitude toward the project. Include if they are unaware, leading, supportive, neutral, or resistant.
Example:
Supportive but needs frequent updates.
Neutral, with limited engagement required.
Resistant to process changes.
4. Interests
Detail the stakeholder’s specific interests, concerns, or expectations about the project outcome.
Example:
Ensure compliance with regulatory standards.
Achieve cost savings through optimized processes.
Interested in employee training opportunities.
5. Level of Impact
Assess the extent to which the stakeholder will be impacted by the project (High, Medium, Low).
Example:
High impact for IT Department due to system changes.
Low impact for the Finance Department.
6. Level of Influence
Indicate the degree of influence the stakeholder holds over project decisions (High, Medium, Low).
Example:
High influence for the Executive Sponsor.
Low influence for front-line staff.
7. Communications Preferences
Specify the stakeholder's preferred method and frequency of communication (e.g., email, phone, meetings).
Example:
Weekly email updates and monthly review meetings.
Real-time messaging via Teams.
Formal reports delivered quarterly.
8. Location
Indicate where the stakeholder or stakeholder group is physically located or working from (if applicable).
Example:
Headquarters, New York.
Remote, working across different time zones.
9. Success Criteria
Define what success looks like for the stakeholder from their perspective. This ensures alignment with their expectations.
Example:
Project completion within budget and timeline.
Improved customer satisfaction by 10%.
Seamless transition to the new system with minimal downtime.
10. Work Hours
Note the working hours or availability of the stakeholder to facilitate scheduling meetings and updates.
Example:
9 AM – 5 PM EST (Monday to Friday).
Flexible, but prefers meetings after 10 AM.

## Example
Stakeholder Register Project: E-Commerce Platform Development Date: 1 August 20xx
# | Stakeholder | Role | Attitude | Interests | Level of Impact | Level of Influence | Communications Preferences | Location | Success Criteria | Work Hours
1 | Fred Martin | Executive Sponsor (CEO) | Supportive | Expand market reach and increase revenue through online sales | High | High | Monthly strategy meetings and executive reports | Corporate Headquarters | Achieving online sales growth in 6 months and increasing market share | 9 AM – 5 PM EST
2 | Sonya Plummer | Project Manager | Supportive | Deliver the project successfully aligned with strategic goals | High | High | Daily updates via email, weekly meetings | Remote with periodic onsite meetings | Completion on time, within scope, and budget | Flexible to accommodate time zones
3 | Peggy Francis | IT Director | Neutral | Ensure platform stability, scalability, and performance | Medium | High | Weekly technical review meetings, email threads | Corporate Headquarters | Seamless integration with minimal downtime | 9 AM – 6 PM EST
4 | Hiroko Kubota | Marketing Manager | Supportive | Expand digital footprint and drive engagement | Medium | Medium | Weekly progress meetings and dashboards | Remote | Significant traffic growth and improved visibility | 9 AM – 4 PM EST
5 | Ahmed Muhammad | Customer Service Manager | Supportive | Enhance customer satisfaction with improved interactions | High | Medium | CRM system reports, email notifications | On-site | Faster resolution times and improved satisfaction ratings | 10 AM – 7 PM EST
6 | Sylvia Samuels | Operations Manager | Supportive | Reduce inefficiencies and streamline operations | Medium | Medium | Email reports, monthly meetings | On-site | Smooth alignment of online and in-store operations | 9 AM – 5 PM EST
7 | Vendor Representative | E-commerce Vendor Representative | Supportive | Ensure smooth implementation and post-launch support | Medium | Medium | Email updates, technical meetings | Off-site | Fully functional platform with minimal bugs at launch | Flexible, on call
8 | Customers (End Users) | End Users | Supportive | Seek seamless shopping experience with excellent service | High collectively, low individually | High collectively, low individually | Email notifications, in-app messages | Multiple regions | 24/7 product availability, efficient service | Accessible 24/7